## Schedule
| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes
1 | EasyDoctor | 65 days | 2022-04-25 08:00 | 2022-08-20 17:00
2 | Project Start | 0 days | 2022-04-25 08:00 | 2022-04-25 17:00
3 | Initiation (Stage 1) | 5 days | 2022-04-25 08:00 | 2022-04-30 17:00 |  |  | Week 1
4 | Prepare Report 1 | 5 days | 2022-04-25 08:00 | 2022-04-30 15:00 | 2 | HuyTPG, SonCT, LongLQ, HuyTV, ThangPHC
5 | Deliver Report 1 (Project Introduction) | 0 days | 2022-04-30 15:00 | 2022-04-30 17:00 | 4
6 | Planning & Requirement (Stage 2) | 10 days | 2022-05-02 08:00 | 2022-05-22 17:00 |  |  | Week 2-4
7 | Project Planning | 5 days | 2022-05-02 08:00 | 2022-04-06 17:00
8 | Prepare Project Plan v0.9 | 5 days | 2022-05-02 08:00 | 2022-05-06 17:00 | 5 | HuyTPG
9 | Deliver Report2 (Project Plan v0.9) | 0 days | 2022-05-06 15:00 | 2022-05-06 17:00 | 8
10 | Project Preparing | 10 days | 2022-05-02 08:00 | 2022-05-22 17:00
11 | Create Technical Prototype | 10 days | 2022-05-02 08:00 | 2022-05-22 17:00 | 8SS | HuyTPG
12 | Technical Training/Self Study | 10 days | 2022-05-02 08:00 | 2022-05-22 17:00 | 11SS | HuyTPG, SonCT, LongLQ, HuyTV, ThangPHC
13 | Requirement Analyzing | 14 days | 2022-05-09 08:00 | 2022-05-22 17:00 |  | HuyTV, ThangPHC
14 | Write SRS v0.9 | 12 days | 2022-05-09 08:00 | 2022-05-20 17:00 | 5
15 | Update Project Plan (v1.0) | 2 days | 2022-05-20 08:00 | 2022-05-22 17:00 | 14FS-2 days
16 | Deliver Report3 (SRS v0.9 + Plan v1.0) | 0 days | 2022-05-22 15:00 | 2022-05-22 17:00 | 14;15
17 | Software Designing (Stage 3) | 10 days | 2022-05-23 08:00 | 2022-06-01 17:00 |  | HuyTV, ThangPHC | Week 5
18 | Write SDS v0.9 | 10 days | 2022-05-23 08:00 | 2022-05-29 17:00 | 5
19 | Update Project Plan (v1.1) | 2 days | 2022-05-28 08:00 | 2022-05-29 17:00 | 18FS-2 days
20 | Deliver Report4 (SDS v0.9 + Plan v1.1) | 0 days | 2022-05-29 15:00 | 2022-05-29 17:00 | 18;19
21 | Implementation (Stage 4) | 30 days | 2022-06-02 08:00 | 2022-07-10 17:00 |  |  | Week 6-11
22 | Code Iteration 1 | 10 days | 2022-06-02 08:00 | 2022-06-12 08:00 |  | HuyTPG, SonCT, LongLQ
23 | Update SRS & SDS (Iteration 1) | 5 days | 2022-06-02 08:00 | 2022-06-07 08:00 | 20
24 | Create Test Cases (Iteration 1) | 5 days | 2022-06-08 08:00 | 2022-06-12 08:00 | 23SS+2 days
25 | Code, UT, IT for Iteration 1 | 8 days | 2022-06-04 08:00 | 2022-06-12 08:00 | 23SS+2 days
26 | Complete Software Package 1 | 0 days | 2022-06-12 15:00 | 2022-06-12 17:00 | 23;24;25
27 | Code Iteration 2 | 10 days | 2022-06-13 08:00 | 2022-06-26 17:00 |  | HuyTPG, SonCT, LongLQ
28 | Update SRS & SDS (Iteration 2) | 5 days | 2022-06-13 08:00 | 2022-06-18 15:00 | 26
29 | Create Test Cases (Iteration 2) | 5 days | 2022-06-19 15:00 | 2022-06-25 15:00 | 28SS+2 days
30 | Code, UT, IT for Iteration 2 | 8 days | 2022-06-18 17:00 | 2022-06-26 17:00 | 28SS+2 days
31 | Complete Software Package 2 | 0 days | 2022-06-26 15:00 | 2022-06-26 17:00 | 28;29;30
32 | Code Iteration 3 | 10 days | 2022-06-27 08:00 | 2022-07-10 17:00 |  | HuyTPG, SonCT, LongLQ
33 | Update SRS & SDS (Iteration 3) | 5 days | 2022-06-27 08:00 | 2022-07-02 17:00 | 31
34 | Create Test Cases (Iteration 3) | 5 days | 2022-07-03 17:00 | 2022-07-10 17:00 | 33SS+2 days
35 | Code, UT, IT for Iteration 3 | 8 days | 2022-07-02 17:00 | 2022-07-10 17:00 | 33SS+2 days
36 | Complete Software Package 3 | 0 days | 2022-07-09 08:00 | 2022-07-09 17:00 | 33;34;35
37 | Deliver Report5 (Test Report) | 0 days | 2022-07-10 17:00 | 2022-07-10 17:00 | 33;34;35
38 | Verification (Stage 5) | 10 days | 2022-07-11 08:00 | 2022-07-24 17:00 |  | All | Week 12-13
39 | Execute ST & Fix Bugs | 10 days | 2022-07-11 08:00 | 2022-07-24 17:00 | 37
40 | Prepare for Deployment | 10 days | 2022-07-11 08:00 | 2022-07-24 17:00 | 39SS
41 | Update Project Documents | 10 days | 2022-07-11 08:00 | 2022-07-24 17:00 | 39SS
42 | Complete Full Software Package | 0 days | 2022-07-24 08:00 | 2022-07-24 17:00 | 39;40;41
43 | Transition (Stage 6) | 10 days | 2022-07-25 08:00 | 2022-08-07 17:00 |  | All | Week 14-15
44 | Software Optimization | 10 days | 2022-07-25 08:00 | 2022-08-07 17:00
45 | Optimize/Refactor Codes | 5 days | 2022-07-25 08:00 | 2022-07-30 08:00 | 42
46 | Execute UAT & Fix Bugs | 5 days | 2022-07-31 08:00 | 2022-08-07 17:00 | 45
47 | Deploy Final Code | 0 days | 2022-08-07 15:00 | 2022-08-07 17:00 | 46
48 | User Guides | 5 days | 2022-08-03 17:00 | 2022-08-07 17:00 |  | HuyTPG
49 | Prepare User Guides | 5 days | 2022-08-03 17:00 | 2022-08-07 17:00 | 45SS
50 | Deliver Report6 (User Guides) | 0 days | 2022-08-03 08:00 | 2022-08-03 17:00 | 49
51 | Preapre Final Project Report | 4 days | 2022-08-03 17:00 | 2022-08-06 17:00 | 50
52 | Prepare Thesis Presentation | 1 day | 2022-08-06 17:00 | 2022-08-07 17:00 | 51
53 | Deliver Report7 (Final Project Report) | 0 days | 2022-08-07 15:00 | 2022-08-07 17:00 | 44;48;51;52
ProjectCode - page2

## Responsibility
Responsibility | HuyTPG | ThangPHC | SonCT | LongLQ | HuyTV
Project Planning & Tracking | D | R | D | R | I
Prepare Project Introduction Document | D | I | R | I | D
Prepare SRS Document (Overview Part) | R | D | I | R | D
Prepare SRS Document (User Requirements) | I | D | R | D | D
Find idea flow patient | D | R | R | D | I
Find idea flow doctor | D | I | D | R | R
Find idea social network | R | D | D | I | I
Find idea payment | I | D | R | D | R
Review knowledge spring boot CRUD | R | I | D | D | I
Review knowledge testing | I | D | R | D | D
Review knowledge SRS | D | D | D | D | D
Make Basic Design | I | D | I | R | D
Draw use-case diagrams | I | I | R | D | D
Sketch, Wireframe UI/UX | R | D | I | I | D
Design database by ERD | D | R | D | D | I
Create schema database | D | R | D | R | I
Mockup, Prototype UX/UI | R | D | I | I | R
Code and review code | D | R | D | D | R
Merge code | R | R | D | D | I
Unit Test | D | R | I | D | D
Create System Test Document | I | D | R | R | D
Fix errors in the whole system | D | R | D | D | I
Prepare Software Test Document | R | D | R | I | D
Prepare Software User Guides | D | R | I | R | D
Demo whole system | D | D | D | D | D
Prepare Final Reports | D | D | D | D | D
Prepare Final Capstone Project Presentation | D | D | D | D | D
Capstone Project Presentation | D | D | D | D | D